## Gantt Chart - Manual Duration
Task Name | Start Date | End Date | Duration (Days) | Days Complete | Days Remaining | Percent Complete | Start Date in Number Form | 42920
Deciding on topic | 2017-07-04 | 2017-07-11 | 7 | 7 | 0 | 100%
Deciding on appropriate title | 2017-07-05 | 2017-07-12 | 7 | 7 | 0 | 100%
Planning which components are required | 2017-07-12 | 2017-07-19 | 7 | 7 | 0 | 100%
Ordering components | 2017-07-19 | 2017-07-26 | 7 | 7 | 0 | 100%
Learning hardware/software bridge | 2017-07-26 | 2017-08-02 | 7 | 7 | 0 | 100%
Building device | 2017-08-02 | 2017-08-09 | 7 | 7 | 0 | 100%
Setting up server | 2017-08-09 | 2017-08-16 | 7 | 7 | 0 | 100%
Port forwarding | 2017-08-16 | 2017-08-23 | 7 | 7 | 0 | 100%
Create webpage | 2017-08-23 | 2017-09-13 | 21 | 21 | 0 | 100%
Time to fix any errors | 2017-09-13 | 2017-09-27 | 14 | 14 | 0 | 100%
Time to improve website | 2017-09-27 | 2017-10-18 | 21 | 21 | 0 | 100%
Write production log | 2017-10-18 | 2018-03-27 | 160 | 160 | 0 | 100%
Write report | 2017-10-25 | 2018-01-26 | 93 | 93 | 0 | 100%
Create presentation | 2018-01-26 | 2018-02-26 | 31 | 31 | 0 | 100%
Rehearse presentation | 2018-01-27 | 2018-02-27 | 31 | 31 | 0 | 100%
Make improvments to full report | 2018-02-27 | 2018-03-13 | 14 | 14 | 0 | 100%
Proof Read & Print | 2018-03-13 | 2018-04-13 | 31 | 31 | 0 | 100%